| Name | Frank Paonessa | Class # | N452 |
| --- | --- | --- | --- |
| Dealership | West Edmonton Volkswagen | Date | 12/14/2024 |

| Current Situation or Challenge to be Addressed: | No pricing strategy creating aged and aging inventory |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Our Used Inventory Stock Analysis is $202588.00 in dead inventory and $553320.00 in old inventory |  |  |
| Goal (what do you want to achieve?) | Our goal is to operate with no aged Inventory over 75 Days |  |  |
| Goal Performance Level (include specific measure) | O Vehicles over 75 Days and 5% of Invenory under 5% |  |  |
| Goal Start Date: | 12/16/2024 | Goal End Date: | 3/31/2025 |
| First Check-in Date: | 1/1/2025 | Performance Objective: | Finish the year with 0 vehicles over 90 Days |
| Second Check-in Date: | 1/31/2025 | Performance Objective: | Finish the month with 0 Vehicles over 85 Days,Lower the % of Old (61-90 days) from 24% to 15% |
| Third Check-in Date: | 2/28/2025 | Performance Objective: | Finish the month with 0 Vehicles over 80 Days,Lower the % of Old (61-90 days) from 25% to 7.5% |
| Fourth Check-in Date: | 3/31/2025 | Performance Objective: | Finish the month with 0 Vehicles over 75 Days,Lower the % of Old (61-90 days) from 7.5% to 5% |
| How does your goal align with the dealers’ vision? | The goal aligns with our Vision of being a Premium Player in the Used Vehicle Market in Edmonton. As well as training our future leaders on how to run a successful and profitable business |  |  |
| What are the potential benefits of achieving your goal? | The potential benefits are numereous. This will free up frozen capital to re-invest in the Used Vehicle department. We will be able to increase the volume of Vehicles that we can Deliver in New and Used increasing the Sales and Finance Gross. We will be able to take on more Inventory increasing the Fixed Operations gross. The Sales team will deliver more vehicles supporting higher commissions and increase staff longevity and lower turnover. |  |  |
| What are the potential consequences if you don’t achieve your goal? | The consequences first and foremost is not hitting our potential for Volume and Gross profit creating a lower net profit and income for everyone that works here at West Edmonton Volkswagen. |  |  |
| Why is the goal important to you? | As a new dealership I understand that the more volume I produce leads to long term success through customer loyalty. It is essential that we master this process for the good of all of our employees no matter what department they work in. We owe everyone we bring on a chance to support there family and create a career opportunity with our organization. |  |  |
| Potential Obstacles | The obstacles boil down to believing in the process. Having a vehicle that is taking in incorrectly (high cost to Market) doesn't help anyone if it is not turned quickly. Holding the management team to a process can also be a problem. Low trades volume can also increase our dependency in using Auctions to supplement Inventory needs. |  |  |
| Potential Solutions | Weekly review of our pricing strategy, adjust payplans to reward success, start Buy-in program to take advantage of service customers not relying on Auctions. |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | If our goal is achieved we will move our monthly used vehicle volume from 52 to 75 by increasing our turn from 7 to 10. We will increase F&I by $51658/Month, Recondition by $36046/Month, Hard Pach by $23000/Month,Other income by $11477/Month, and a Front end variance of $15560/month increasing our potential by $137740/Month or $1652883/Year |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Review of current affairs and strategies on Inventory and Pricing Strategy | -VAuto Review -Pre-Owned Stock Analysis -Sales Log analysis | Frank Paonessa | Clear understanding of where we are and where we are going | December 13 , 2024 8:00 - 10:00 |
| Create Pricing Strategy | VAuto | Frank Paonessa John Mallari Josh LUYIMBAZI | Create a Pricing Strategy that we can hold the department accountable to | December 14 , 2024 8:00 - 10:00 |
| Re-set all Used Vehicle pricing | -VAuto | John Mallari Josh LUYIMBAZI | Entire Inventory priced as Strategy dictated | December 16, 2024 8:00 |
| Pricing Strategy Review with entire Sales Team | -VAuto -Pre-Owned Stock Analysis -Sales Log analysis | John Mallari Josh LUYIMBAZI | Entire team understanding strategy | December 21, 2024 8:00 |
| Wholesale all vehicles over 90 days | Adesa Auction | Josh LUYIMBAZI | 0 Aged Inventory by December 31, 2024 | December 31, 2024 |
| Weekly VAuto review | VAuto Pricing Strategy | Frank Paonessa John Mallari Josh LUYIMBAZI | Reduced old Inventory $0 Frozen Capital Increase turn Increase Ued retail from 52 to 75 | December 19, 2024 Weekly review every Thursday at 1:00 |
| Finance Statement Review | Financial Statement Finance Statement Review Document | Frank Paonessa John Mallari Josh LUYIMBAZI | Frank Paonessa John Mallari Josh LUYIMBAZI | January 15, 2025 Monthly review after every statement |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Since starting NADA these action plans have been the corner stone of how we operate. The one underlying principle is measuring our results. We have made measuring a daily, weekly and monthly part of our culture. We created routines for everyone to ensure we do not lose focus on key matrix's that are important to us and our success. "What gets measured, Gets done. What Doesn't get measured, gets forgotten"

Describe any planning or implementation meetings conducted as part of development of your plan.

The biggest win was getting all the Managers to take part in creating the Pricing Strategy and inturn conducting a entire Sales meeting with all staff to review. Getting everyone on the same page was critical. The big thing was being able to explain the "Why" so that moving forward everyone was rowing in the same direction.

| Sponsor Signature: |  |
| --- | --- |