| Name | Nelson Lyles | Class # | NADA 421 |
| --- | --- | --- | --- |
| Dealership | Withers Automotive CDJR of Lawrenceburg | Date | 11/1/2023 |

| Current Situation or Challenge to be Addressed: | Variable Sales Expense *Floor Plan Intresest Rate *Personnel number of employees is to high & compensation needs to be restructered |  |  |
| --- | --- | --- | --- |
| Current Performance Level (include specific measure): | Variable Sales Expense is currently 79.3% GP on New and 84% GP on Preowned Floor plan intrest rate is curerently 9.5% apr non captive. This translates to 66% GP on new and 77% GP on preowned including inventory curtailments. Currently we have 52 full time employees, we need to reduce this number by 20%, bringing our employee count to 42. This will also aid in the restructering of comp and reduce expense. |  |  |
| Goal (what do you want to achieve?) | Reduce the Variable Sales Expense by 20% Change our current Non Captive floor plan provider to Captive provider Stellantis Restructer department staffing, and restructer compensation plans |  |  |
| Goal Performance Level (include specific measure) | Our current non captive floor plan rate is 9.5% by changing to capitive (Stellantis)it will reduce to 7%, saving us 2.5%. Reducing our staffing by 20% will reduce montlhy comp by $27,040.00 or annual comp by $54,080.00 Reduce the variable sales expense %GP by 20% |  |  |
| Goal Start Date: | 10/1/2023 | Goal End Date: | 1/1/2024 |
| First Check-in Date: | 11/1/2023 | Performance Objective: | Contact Stellantis on Capitive Floor Plan Conduct aa detailed expense analysis Review and negotiate vendor contracts Implement performance based pay plans |
| Second Check-in Date: | 12/1/2023 | Performance Objective: | Click or tap here to enter text. |
| Third Check-in Date: | 12/1/2023 | Performance Objective: | Submit application to Stellantis Have employee staffing count to 42 Set specific targets for expense catagories Monitoring and reporting |
| Fourth Check-in Date: | 1/1/2024 | Performance Objective: | Approval finalized with Stellantis switching ou floor plan from non captive to captive. Employee count solid at 42 or less. New pay plans implemented. Continous improvement |
| How does your goal align with the dealers’ vision? | These cost cutting measures align with our overall business strategy. |  |  |
| What are the potential benefits of achieving your goal? | Reduce expenses and become more profitable and effecient |  |  |
| What are the potential consequences if you don’t achieve your goal? | Minmal profits |  |  |
| Why is the goal important to you? | Cutting expenses and managing expense is vitatly important to the success of any dealership. |  |  |
| Potential Obstacles | Lack of buy in, and lack of consistentcy, poor communication |  |  |
| Potential Solutions | Employee invovement nd feedback, regular monitoring and reporting,training and skill development |  |  |
| BOTTOM LINE! Financial Impact of Achieving Your Goal (expressed in dollars) | The overall finicial impact will be a savingings of $146,490.40 |  |  |

What specific actions or steps will you take to accomplish your goal?  What will you do differently or improve? For each, be sure to include necessary resources, who is accountable, the measurable result, and dates.

| Specific action/step | Necessary resource(s) | Accountable person(s) | Expected result | Start, End, & CHeckpoint Dates |
| --- | --- | --- | --- | --- |
| Contact Stellantis to secure floor plan | Stellantis Rep | Lisa Heil, Controller | Application for floor plan | Nov1st to Dec 1st |
| Conduct a detailed expense anaylsis | Accounts payable FCA Statement FCA operating Expense Profile | Nelson Lyles, GM | 20% reduction in variable sales expense | Nov 1st to Jan !st |
| Implement new pay plans and restructer employee staffing | FCA Statement Payroll records HR Director | Lisa Heil, Controller Patty Henderson, HR Nelson Lyles, GM | New Pay Plans Reduction in staffing and comp by 20% | Nov1st to Dec 1st |
| Monitore and Reporting | Meeting minutes Data reporting | Lorena Romero Thersa Calis | Improve consistency in communication. Employee buy in and understanding | Nov1st to Jan1st |
| Set specific targets for expense catagories | General Ledger FCA Statement FCA Operating and Expense Profile | Nelson Lyles, GM Lisa Heil, Controller | Clear and transparent catagories | Nov1st to Dec 1st |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |
| Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. | Click or tap here to enter text. |

As you work toward your goal, it’s important to have interim check points with specific, measurable objectives so your team can hold themselves accountable. If everyone knows the goal and objectives, you don’t have to spend your valuable time micromanaging.

Once you’ve accomplished your goal, added or adjusted policies, procedures, and behaviors, now what? How will you ensure you and your staff do not fall back into the previous habits that produced poor results? Be specific.

Breaking bad habits and forming new ones is an ongoing process that requires commitment and effort from everyone involved in our team. We need to provide continuous training, a positive enviroment, and establish accountability that holds our team accountable for our actions. We also need to encourage open communication that allows team members to feel comfortable expressing their thoughts and concerns so we can address issues before they become ingrained habits.

Describe any planning or implementation meetings conducted as part of development of your plan.

Launch meeting: 1. Set Clear Goals and Objectives 2. Establish Accountability 3. Implement Systems and Processes 4. Regularly Reassess Strategies 5. Provide Resources and Support

| Sponsor Signature: |  |
| --- | --- |