## Slide 1: Performance Action Plan Collision Center - Parts
Submitted by a former student

## Slide 2: Ordering Parts
Identification & Communication Process

## Slide 3: The Current Situation
There is a breakdown in the communication process between the technician, parts department and estimator when a part is ordered.
Documentation procedures are not followed correctly to indicate a part has been ordered.
This is creating a negative impression for the customer when they receive communication from the Update Plus or call center about a situation they were not informed of.

## Slide 4: The Overall Objective
Implement a process to ensure that the Estimator is informed when their parts are ordered and why.
For the Estimator to inform the customer that the parts have been ordered and properly documented on the repair order.
Opportunity to set the expectation with the customer that once the parts have been received they will be contacted to schedule an appointment for installation.

## Slide 5: Proposed Timeline
July 6th - Process Meeting
  Attendees: Collision Mgr, Parts Mgr, Technician Team Lead & chosen Estimator
    Discuss the current situation.
    Troubleshoot thru possible solutions.
    Agree upon an action plan to begin implementing.
    Establish “To-Do” items following meeting.
July 7th - Process Meeting
  Attendees: Collision, Parts Mgr, Technician Team Lead & chosen Estimator
    Finalize the process.
    Discuss & plan for implementation.
July 8th – Rollout Meeting (10am & 2pm Meeting to allow for full participation)
  Attendees: All Collision & Parts Personnel (must attend one of the sessions)
    Present new process and expectations.
    Train process
    Encourage feedback once implemented.
July 9th – Live with new Parts Ordering Communication Process
July 10th – Feedback Request
    Ask for feedback from all personnel before follow up meeting with managers.
July 17th – Follow-Up Meeting
  Attendees: Collision Mgr, Parts Mgr, Technician Team Lead & chosen Estimator
    Discuss feedback received.
    Discuss revisions needed to be made.
    Compile Revise process
    Communicate Final Process to Service & Parts Personnel
    Proceed with monitoring process to ensure it is being followed.

## Slide 6: Action Plan “The Process”
  Parts Ordering Identification & Communication Process
Technician identifies a part is needed to repair the vehicle.
Technician relays to the Parts Department which item is needed.
  Via phone, voice, or Profitnet
Technician makes notes in Profitnet, or manual on RO as to the status of the vehicle.
The Parts Department locates the part to see if it is in stock.
  If in stock the vehicle repair is completed.
  If not in stock then a locator search is run to find out when it will arrive.
The Parts Department communicates to the Consultant.
  Via phone, voice, or Profitnet
The “OK to order” Flag is then selected in Profitnet by the Parts Representative and notes added for the Service Consultant.
The Parts are then ordered.
The Estimator informs the customer as to the status of the repairs and the special order part that is going to be required.
Estimator properly documents the RO in Profitnet, and selects the proper indicators to relay to all others the parts are ordered and a projected delivery date.
Once the part arrives the Estimator will then review the estimate and workload and contact the customer to schedule the appointment.

## Slide 7: Requirements
#1 Meeting with Collision Center
    Collision Manager, Parts Manager, Technician Team Leader & Estimator
  Action Proposed
    A through process for Parts ordering and Communication
#2 Meeting with Stakeholder(s) (dealership personnel)
    Collision Management Team
    Estimators
    Body Technicians
    Parts Manager
  Describe what is in place to support desired goal
    Written process for Parts Ordering and Communication
    Parts Order Flag implemented within the Profitnet system
    Utilize Notes within the Profitnet system
    “Parts Ordered” ink stamp to be used on the RO to provide information from parts to the Technician and Estimator
    Correct Verbiage for RO documentation
      To ensure the customer is informed on the invoice
      Call Center/Estimator will be able to interpret what was ordered and communicate with the customer professionally during scheduling.
#3 Accountability: Monitoring Progress:
    Who: Collision Manager & Parts Manager
    What: Review Parts Ordering on RO’s daily/weekly to ensure documentation procedures are being followed.
    By When: Daily as of July 13th until final process is completed on July 17th. Will then monitor weekly.

## Slide 8: Requirements Continued…
#4 Established Checkpoints for Measuring Progress
    Daily/Weekly Review of RO’s to ensure documentation process is being followed.
    Daily/Weekly Review of Profitnet Notes & documentation
    Continued Feedback from Service & Parts team as concerns/suggestions arrise.
    Feedback from Estimator as to the reaction they have received from the customers when reaching out to schedule their Parts Ordering.
#5 Estimated Cost for Implementation
    $24.56 to purchase a customized Parts Stamp for the RO
    Management & Department time to ensure process was implemented
    Management time to ensure process continues to be followed
Projected Date of Completion
  August 1, 2015