# Departmental Action Plan Template

Student Name: Robert Milner

Class & Student Number: 324-40

Academy Week (Var II): 5

# Current situation or challenge you want to address based on the Jennifer Suzuki Outline: (must be quantifiable)

Outgoing phone call guides are outdated

# Overall Objective and Specific Desired Results:

Improve:

- Customer experience—Improve Sales CSI to 190

- Appointment set ratio—Improve to 35%

- Appointment show ratio—Improve to 60%

- Appointment delivery ratio—Improve to 15%

# Describe your action plan in detail (be specific and include before and after measurements)

- Post current “BEFORE” KPI’s

- CSI Score------------Q4 Sales CSI Score is 182.63

- Appointment set ratio %----Q4 Set ratio is 29.17%

- Appointment show ration %----Q4 Show ratio is 55.89%

- Appointment delivery ratio %-Q4 Delivery ratio is 9.85%

- Partner with BDC Director to Re write outgoing phone call guides that are used by BDC agents and salespeople

- Program new guides in CRM

- Train all BDC agents and sales people on new call guides

- Roll play with each person authorized to make calls to evaluate comprehension level

- Post updated “AFTER” KPI’s

- CSI Score

- Appointment set ratio %

- Appointment show ration %

- Appointment delivery ratio %

# Timeline:

Jan 1st 2018………Have call Guides re written ----completed on time

Jan 8th 2018……..Have Guides programed in CRM and begin training----Completed on time

Jan 15th 2018…..Do roll pay with authorized callers and evaluate proficiency---Currently underway as of 01/12

Jan 22nd 2018….exclusive new Guide utilization----On Schedule

April 1st 2018…. Measure and post updated:

- Customer experience—Sales CSI goal---190

- Appointment set ratio—Appointment set ratio goal 35%

- Appointment show ratio—Appointment show ratio goal 60%

- Appointment delivery ratio—Delivery ratio goal 15%

# Meeting with Stakeholders (dealership personnel)

Describe what behavior change is needed to support desired goal.  Address required coaching, training and/or consequences (PINO, Gain, Pain).  Include timelines / Accountability / Monitoring process

- Who:BDC Director, Sales Manager and BDC agents

- What:Willingness to improve on call guides that they worked hard to create, have confidence in and have been utilizing for years

- By When:Mid January

- How:Utilize updated training materials